## Feuille1
Meetings	06/02/16	19/03/16

				JR		HS
Subproject	Task	Deadline	Deliverable	ETA	ETW	ETA	ETW
Board Game	Board game design	ok
	External events	01/03/16
	Game test	01/04/16
	Construction	15/04/16
	Final version	09/05/16
Computer Game	Basic model	ok
	Calibration	01/03/16
	Interactive model	01/04/16
	Web version	09/05/16
	Model description	09/05/16			6
Redaction	Abstract	ok	abstract		3
	Poster	09/05/16	poster
	Website	01/04/16